## Sheet1
BugID | TestID | Description | Severity(1 to 3) | Assigned | Completed Date
1 | ui.2 | doesn’t check for duplicate usernames | 2 | Adriana | December 4th, 2017
2 | ui.1 | Movies without posters would cause results to not return | 2 | Taylor/ Adriana | December 3rd, 2017
3 | ui.1 | Wouldn't check database to see if it's a valid username | 3 | Adriana | December 1st, 2017
4 | ui.1 | Twitter username wouldn't load into database | 1 | Adriana | December 4th, 2017
5 | ui.1 | Movie database api wasn't parsing correctly | 1 | Taylor/ Adriana | December 3rd, 2017
6 | ui.1 | Word frequency algorithm was analyzing by characters instead of words | 2 | Adriana | November 30th, 2017